## Crescimento
#VALUE!
|  | Mês: | 2024-12-01 |  | →Menu←
|  | Trim: | 4T24
Crescimento
| Leilões | Projetos | Contrato | Empresa | % ISA ENERGIA BRASIL | UF | Deságio | RAP ISA ENERGIA BRASIL Ciclo 2024/2025 (R$ milhões) | Assinatura do Contrato | Data de Necessidade¹ | Prazo ANEEL | Investimento ANEEL (R$ milhões) | CapEx ANEEL Participação ISA ENERGIA BRASIL data base leilão (R$ milhões) | CapEx ISA ENERGIA BRASIL total até 31/12/2024 (R$ milhões) | Licenci. Ambiental (LI) | Início da Construção | Avanço Fundiário³ | Avanço Físico4 | Entrada em Operação Comercial²
Paraguaçu | 013/2015 (out/2016) | Paraguaçú (Lote 3) | 003/2017 | IE Paraguaçu | 50% | BA/MG | 0% | 77.0818 | 2017-02-10 | 2019-01-01 | 2022-02-10 | 509.595 | 254.7975 | 333.359 | ü | 2T19 | 100% | 100% | 3T22
Aimorés |  | Aimorés (Lote 4) | 004/2017 | IE Aimorés | 50% | MG | 0% | 51.6448 | 2017-02-10 | 2019-01-01 | 2022-02-10 | 341.118 | 170.559 | 197.5455 | ü | 2T19 | 100% | 100% | 2T22
Itaúnas |  | Itaúnas (Lote 21) | 018/2017 | IE Itaúnas | 100% | ES | 25.14% | 68.4674 | 2017-02-10 | 2018-07-01 | 2022-06-10 | 297.819 | 297.819 | 373.803 | ü | 3T18 | 100% | 100% | 4T23
Ivaí | 005/2016 (abr/2017) | Ivaí (Lote 1) | 022/2017 | IE Ivaí | 50% | PR | 33.24% | 189.2949 | 2017-08-11 | 2021-02-01 | 2022-08-11 | 1936.4738 | 968.2369 | 1050.4335 | ü | 4T19 | 100% | 100% | 4T22
Tibagi |  | Tibagi (Lote 5) | 026/2017 | IE Tibagi | 100% | SP / PR | 32.2% | 22.4741 | 2017-08-11 | 2017-01-01 | 2021-08-11 | 134.6464 | 134.6464 | 117.526 | ü | 3T18 | 100% | 100% | 4T20
Itaquerê |  | Itaquerê (Lote 6) | 027/2017 | IE Itaquerê | 100% | SP / PR | 44.51% | 67.218 | 2017-08-11 | 2018-06-01 | 2021-08-11 | 397.7335 | 397.7335 | 255.906 | ü | 3T18 | 100% | 100% | 3T20
Aguapeí |  | Aguapeí (Lote 29) | 046/2017 | IE Aguapeí | 100% | SP / PR | 52.69% | 75.9335 | 2017-08-11 | 2018-12-01 | 2021-08-11 | 601.8795 | 601.8795 | 363.42 | ü | 3T19 | 100% | 100% | 1T21
Itapura-Bauru |  | Bauru (Lote 25) | 042/2017 | IE Jaguar 6 | 100% | SP | 57.55% | 15.3352 | 2017-08-11 | 2019-08-01 | 2021-02-11 | 125.7943 | 125.7943 | 62.978 | ü | 2T18 | 100% | 100% | 3T19
Itapura-Lorena | 002/2018 (jun/2018) | Lorena (Lote 10) | 021/2018 | IE Itapura | 100% | SP | 73.9% | 17.3654 | 2018-09-21 | 2020-01-01 | 2022-09-21 | 237.947 | 237.947 | 126.087 | ü | 3T19 | 100% | 100% | 4T21
Biguaçu |  | Biguaçu (Lote 1) | 012/2018 | IE Biguaçu | 100% | SC | 66.7% | 53.4445 | 2018-09-21 | 2021-09-01 | 2023-09-21 | 641.382 | 641.382 | 455.965 | ü | 1T21 | 100% | 100% | 3T22
Minuano | 002/2019 (dez/2019) | Minuano (Lote 1) | 001/2020 | Evrecy | 100% | RS | 66.85% | 50.2175 | 2020-03-01 | 2020-01-01 | 2025-03-20 | 681.55 | 681.55 | 737.044 | ü | 3T22 | 100% | 100% | 4T24
Três lagoas |  | Três Lagoas (Lote 6) | 006/2020 | IE Tibagi | 100% | MS / SP | 68.12% | 7.0724 | 2020-03-01 | 2020-01-01 | 2023-09-01 | 98.792 | 98.792 | 87.068 | ü | 2T21 | 100% | 100% | 2T22
Triângulo Mineiro |  | Triângulo Mineiro (Lote 7) | 007/2020 | IEMG | 100% | MG | 65.4% | 43.7515 | 2020-03-01 | 2020-01-01 | 2025-03-20 | 553.567 | 553.567 | 519.595 | ü | 1T22 | 100% | 100% | 3T23
Riacho Grande | 001/2020 (dez/2020) | Riacho Grande (Lote 7) | 005/2021 | IE Riacho Grande | 100% | SP | 57.9% | 88.4073 | 2021-03-01 | 2026-01-01 | 2026-03-31 | 1140.628 | 1140.628 | 530.1434 | ü | 3T23 | 100% | 80.4% | -
Piraquê | 001/2022 (jun/2022) | Piraquê (Lote 3) | 008/2022 | ISA CTEEP | 100% | MG / ES | 46.75% | 325.7707 | 2022-09-01 | 2026-01-01 | 2027-09-30 | 3653.6077 | 3653.6077 | 1620.5335 | ü | 3T24 | 96% | 36.84% | -
Jacarandá |  | Jacarandá (Lote 6) | 011/2022 | IE Jaguar 8 | 100% | SP | 59.21% | 15.3151 | 2022-09-01 | 2026-03-30 | 2026-03-30 | 232.2923 | 232.2923 | 35.4809 | ü | 3T24 | 61% | 49.13% | -
Serra Dourada | 001/2023 (jun/2023) | Serra Dourada (Lote 1) | 006/2023 | ISA CTEEP | 100% | BA/MG | 44.85% | 305.553 | 2023-09-01 | Imediata | 2029-03-29 | 3157 | 3157 | 211.901 | 4T25 | 2T26 | 50% | 16.54% | -
Itatiaia |  | Itatiaia (Lote 7) | 012/2023 | ISA CTEEP | 100% | RJ/MG | 41.81% | 235.6417 | 2023-09-01 | Imediata | 2029-03-29 | 2342.2975 | 2342.2975 | 95.892 | 3T25 | 4T25 | 49% | 19.93% | -
Água Vermelha |  | Água Vermelha (Lote 9) | 014/2023 | IE Tibagi | 100% | SP | 50.36% | 8.0324 | 2023-09-01 | Imediata | 2026-09-29 | 94.1769 | 94.1769 | 34.813 | ü | 3T24 | 100% | 58.78% | -
| Total (19) | [5 empty] | 47.16% | 1718.0213 | - | - | - | 17178.2999 | 15784.7065 | 7209.4937 | - | - | - | - | -
¹ Conforme contrato de concessão
²Avanço Fundiário: evolução das propriedades liberadas
³ Avanço Fundiário: evolução das propriedades liberadas
4 Avanço do Projeto: evolução de todas as atividades relativas ao empreendimento até sua energização
çl

## Growth
#VALUE!
| Mês: | 2024-12-01 |  | →Menu←
| Trim: | 4T24
Growth
Auctions | Project | Contract | Company | % ISA ENERGIA BRASIL | UF | Discount | RAP ISA ENERGIA BRASIL Cycle 2024/2025 (R$ million) | Contract signature | Deadline ANEEL | Necessity Date¹ | ANEEL CAPEX (R$ million) | ANEEL CAPEX ISA ENERGIA BRASIL Participation (R$ million) | Total CapEx ISA ENERGIA BRASIL until 12/31/2024 (R$ million) | Environmental License (LI) | Initiation of Construction | Land Development4 | Projects Development5 | Entry in Commercial Operation
ANEEL
013/2015 (oct/2016) | Paraguaçú (Lot 3) | 003/2017 | IE Paraguaçu | 50% | BA/MG | 0% | 77.0818 | 2017-02-10 | 2022-02-10 | 2019-01-01 | 509.595 | 254.7975 | 333.359 | ü | 2Q19 | 100% | 100% | 3Q22
| Aimorés (Lot 4) | 004/2017 | IE Aimorés | 50% | MG | 0% | 51.6448 | 2017-02-10 | 2022-02-10 | 2019-01-01 | 341.118 | 170.559 | 197.5455 | ü | 2Q19 | 100% | 100% | 2Q22
| Itaúnas (Lot 21) | 018/2017 | IE Itaúnas | 100% | ES | 25.14% | 68.4674 | 2017-02-10 | 2022-06-10 | 2018-07-01 | 297.819 | 297.819 | 373.803 | ü | 3Q18 | 100% | 100% | 4Q23
005/2016 (apr/2017) | Ivaí² (Lot 1) | 022/2017 | IE Ivaí | 50% | PR | 33.24% | 189.2949 | 2017-08-11 | 2022-08-11 | 2021-02-01 | 1936.4738 | 968.2369 | 1050.4335 | ü | 4Q19 | 100% | 100% | 4Q22
| Tibagi (Lot 5) | 026/2017 | IE Tibagi | 100% | SP / PR | 32.2% | 22.4741 | 2017-08-11 | 2021-08-11 | 2017-01-01 | 134.6464 | 134.6464 | 117.526 | ü | 3Q18 | 100% | 100% | 4Q20
| Itaquerê (Lot 6) | 027/2017 | IE Itaquerê | 100% | SP / PR | 44.51% | 67.218 | 2017-08-11 | 2021-08-11 | 2018-06-01 | 397.7335 | 397.7335 | 255.906 | ü | 3Q18 | 100% | 100% | 3Q20
| Aguapeí (Lot 29) | 046/2017 | IE Aguapeí | 100% | SP / PR | 52.69% | 75.9335 | 2017-08-11 | 2021-08-11 | 2018-12-01 | 601.8795 | 601.8795 | 363.42 | ü | 3Q19 | 100% | 100% | 1Q21
| Bauru (Lot 25) | 042/2017 | IE Jaguar 6 | 100% | SP | 57.55% | 15.3352 | 2017-08-11 | 2021-02-11 | 2019-08-01 | 125.7943 | 125.7943 | 62.978 | ü | 2Q18 | 100% | 100% | 3Q19
002/2018 (jun/2018) | Lorena (Lot 10) | 021/2018 | IE Itapura | 100% | SP | 73.9% | 17.3654 | 2018-09-21 | 2022-09-21 | 2020-01-01 | 237.947 | 237.947 | 126.087 | ü | 3Q19 | 100% | 100% | 4Q21
| Biguaçu (Lot 1) | 012/2018 | IE Biguaçu | 100% | SC | 66.7% | 53.4445 | 2018-09-21 | 2023-09-21 | 2021-09-01 | 641.382 | 641.382 | 455.965 | ü | 1Q21 | 100% | 100% | 3Q22
002/2019 (dec/2019) | Minuano (Lot 1) 6 | 001/2020 | Evrecy | 100% | RS | 66.85% | 50.2175 | 2020-03-01 | 2025-03-20 | 2020-01-01 | 681.55 | 681.55 | 737.044 | ü | 1Q22 | 100% | 100% | -
| Três Lagoas (Lot 6) | 006/2020 | IE Tibagi | 100% | MS / SP | 68.12% | 7.0724 | 2020-03-01 | 2023-09-01 | 2020-01-01 | 98.792 | 98.792 | 87.068 | ü | 2Q21 | 100% | 100% | 2Q22
| Triângulo Mineiro (Lot 7) | 007/2020 | IEMG | 100% | MG | 65.4% | 43.7515 | 2020-03-01 | 2025-03-20 | 2020-01-01 | 553.567 | 553.567 | 519.595 | ü | 1Q22 | 100% | 100% | 3Q23
001/2020 (dec/2020) | Riacho Grande (Lot 7) | 005/2021 | IE Riacho Grande | 100% | SP | 57.9% | 88.4073 | 2021-03-01 | 2026-03-31 | 2026-01-01 | 1140.628 | 1140.628 | 530.1434 | ü | 4Q23 | 100% | 80.4% | -
001/2022 (jun/2022) | Piraquê (Lot 3) | 008/2022 | ISA CTEEP | 100% | MG / ES | 46.75% | 325.7707 | 2022-09-01 | 2027-09-30 | 2026-01-01 | 3653.6077 | 3653.6077 | 1620.5335 | 3Q24 | 4Q23 | 96% | 36.84% | -
| Jacarandá (Lot 6) | 011/2022 | IE Jaguar 8 | 100% | SP | 59.21% | 15.3151 | 2022-09-01 | 2026-03-30 | 2026-03-30 | 232.2923 | 232.2923 | 35.4809 | 2Q24 | 4Q23 | 61% | 49.13% | -
001/2023 (jun/2023) | Serra Dourada (Lot 1) | 006/2023 | ISA CTEEP | 100% | BA/MG | 44.85% | 305.553 | 2023-09-01 | 2029-03-29 | immediate | 3157 | 3157 | 211.901 | 3Q25 | 3Q25 | 50% | 16.54% | -
| Itatiaia (Lot 7) | 012/2023 | ISA CTEEP | 100% | RJ/MG | 41.81% | 235.6417 | 2023-09-01 | 2029-03-29 | immediate | 2342.2975 | 2342.2975 | 95.892 | 3Q25 | 3Q25 | 49% | 19.93% | -
| Água Vermelha (Lot 9) | 014/2023 | IE Tibagi | 100% | SP | 50.36% | 8.0324 | 2023-09-01 | 2026-09-29 | Imediata | 94.1769 | 94.1769 | 34.813 | 2Q24 | 2Q24 | 100% | 58.78% | -
Total (19) | [5 empty] | 47.16% | 1718.0213 | - | - | - | 7698.9255 | 15784.7065 | 7209.4937 | 15784.7065 | 7209.4937 | - | - | -
¹ According to concession agreement
² To receive the total amount of RAP
3 Land Development: evolution of properties released
4 Project Development: evolution of all activities related to the project until electricity is provided to it

## Greenfield PTBR
#VALUE!
|  | Mês: | 2024-12-01 |  | →Menu←
|  | Trim: | 4T24
Greenfield
| Leilão (data) | Lote | Projeto | Situação Atual | Contrato | Empresa | % ISA ENERGIA BRASIL | Investimento ANEEL (R$ MM) | Investimento ANEEL Participação ISA ENERGIA BRASIL (R$ milhões) | RAP ISA ENERGIA BRASIL Ciclo 2024/2025 (R$ milhões) | Obras |  | Antecip. (meses) | CapEx ISA ENERGIA BRASIL até 31/12/2024 (R$ milhões) | Eficiência CapEx Real (vs ANEEL)
[11 empty] | Início | Fim
Paraguaçu | 013/2015 (out/2016) | 3 | Paraguaçu | Operacional | 003/2017 | IE Paraguaçu | 50% | 509.595 | 254.7975 | 77.0818 | 2T19 | 3T22 | -5 | 333.359 | -12.29%
Aimorés |  | 4 | Aimorés | Operacional | 004/2017 | IE Aimorés | 50% | 341.118 | 170.559 | 51.6448 | 2T19 | 2T22 | -3 | 197.5455 | -0.8417%
Itaúnas |  | 21 | Itaúnas | Operacional | 018/2017 | IE Itaúnas | 100% | 297.819 | 297.819 | 68.4674 | 3T18 | 4T23 | -10 | 373.803 | -4.568%
Ivaí | 005/2016 (abr/2017) | 1 | Ivaí | Operacional | 022/2017 | IE Ivaí | 50% | 1936.4738 | 968.2369 | 189.2949 | 4T19 | 4T22 | -3 | 1050.4335 | 9.501%
Tibagi |  | 5 | Tibagi | Operacional | 026/2017 | IE Tibagi | 100% | 134.6464 | 134.6464 | 22.4741 | 3T18 | 4T20 | 8 | 117.526 | 20.16%
Itaquerê |  | 6 | Itaquerê | Operacional | 027/2017 | IE Itaquerê | 100% | 397.7335 | 397.7335 | 67.218 | 3T18 | 3T20 | 11 | 255.906 | 40.78%
Aguapeí |  | 29 | Aguapeí | Operacional | 046/2017 | IE Aguapeí | 100% | 601.8795 | 601.8795 | 75.9335 | 3T19 | 1T21 | 6 | 363.42 | 46.15%
Itapura-Bauru |  | 25 | Bauru | Operacional | 042/2017 | IE Jaguar 6 | 100% | 125.7943 | 125.7943 | 15.3352 | 2T18 | 3T19 | 18 | 62.978 | 53.5%
Itapura-Lorena | 002/2018 (jun/2018) | 10 | Lorena | Operacional | 021/2018 | IE Itapura | 100% | 237.947 | 237.947 | 17.3654 | 3T19 | 4T21 | 11 | 126.087 | 52.12%
Biguaçu |  | 1 | Biguaçu | Operacional | 012/2018 | IE Biguaçu | 100% | 641.382 | 641.382 | 53.4445 | 1T21 | 3T22 | 13 | 455.965 | 38.89%
Minuano | 002/2019 (dez/2019) | 1 | Minuano | Operacional | 001/2020 | Evrecy | 100% | 681.55 | 681.55 | 50.2175 | 3T22 | 4T24 | 4 | 737.044 | 14%
Três lagoas |  | 6 | Três lagoas | Operacional | 006/2020 | IE Tibagi | 100% | 98.792 | 98.792 | 7.0724 | 2T21 | 2T22 | 12 | 87.068 | 21.64%
Triângulo Mineiro |  | 7 | Triângulo Mineiro | Operacional | 007/2020 | IEMG | 100% | 553.567 | 553.567 | 43.7515 | 1T22 | 3T23 | 20 | 519.595 | 23.63%
Riacho Grande | 001/2020 (dez/2020) | 7 | Riacho Grande | Em Obras | 005/2021 | IE Riacho Grande | 100% | 1140.628 | 1140.628 | 88.4073 | 3T23 | - | - | 530.1434 | -
Piraquê | 001/2022 (jun/2022) | 3 | Piraquê | Em Obras | 008/2022 | ISA ENERGIA BRASIL | 100% | 3653.6077 | 3653.6077 | 325.7707 | 3T24 | - | - | 1620.5335 | -
Jacarandá | 0 | 6 | Jacarandá | Em Obras | 011/2022 | IE Jaguar 8 | 100% | 232.2923 | 232.2923 | 15.3151 | 3T24 | - | - | 35.4809 | -
Serra Dourada | 001/2023 (jun/2023) | 1 | Serra Dourada | Licenciamento Ambiental | 006/2023 | ISA ENERGIA BRASIL | 100% | 3157 | 3157 | 305.553 | 2T26 | - | - | 211.901 | -
Itatiaia |  | 7 | Itatiaia | Licenciamento Ambiental | 012/2023 | ISA ENERGIA BRASIL | 100% | 2342.2975 | 2342.2975 | 235.6417 | 4T25 | - | - | 95.892 | -
Água Vermelha |  | 9 | Água Vermelha | Em Obras | 014/2023 | IE Tibagi | 100% | 94.1769 | 94.1769 | 8.0324 | 3T24 | - | - | 34.813 | -
| Projetos em Operação (13) | [7 empty] | 5164.7041 | 739.3011 | - | - | 2.5761 | 4680.73 | 23.2%
| Controladas 100% em Operação (9) | [7 empty] | 3771.1107 | 421.2796 | - | - | 7.1514 | 3099.392 | 30.52%
| Controladas em Conjunto em Operação (3) | [7 empty] | 1393.5934 | 318.0215 | - | - | -3.4848 | 1581.338 | 4.219%
| Projetos em Construção (6) | [7 empty] | 10620.0024 | 978.7202 | - | - | - | 2528.7637 | -
| Total (19) | [6 empty] | 17178.2999 | 15784.7065 | 1718.0213 | - | - | 2.5761 | 7209.4937 | 23.2%
0

## Greenfield ENG
#VALUE!
|  | Mês: | 2024-12-01 |  | →Menu←
|  | Trim: | 4T24
Greenfield
| Auctions (Date) | Lot | Project | Current situation | Contract | Company | % ISA CTEEP | Investimento ANEEL (R$ MM) | ANEEL Investiment ISA ENERGIA BRASIL Participation (R$ million) | RAP ISA CTEEP Cycle 2024/2025 (R$ million) | Constructions |  | Antecipation (Months) | CapEx ISA ENERGIA BRASIL accumulated until 12/31/2024 (R$ million) | CapEx Efficiency (vs ANEEL)
[11 empty] | Beginning | Conclusion
Paraguaçu | 013/2015 (oct/2016) | 3 | Paraguaçu | Operational | 003/2017 | IE Paraguaçu | 50% | 509.595 | 254.7975 | 77.0818 | 2Q19 | 3Q22 | -5 | 333.359 | -12.29%
Aimorés |  | 4 | Aimorés | Operational | 004/2017 | IE Aimorés | 50% | 341.118 | 170.559 | 51.6448 | 2Q19 | 2Q22 | -3 | 197.5455 | -0.8417%
Itaúnas |  | 21 | Itaúnas | Operational | 018/2017 | IE Itaúnas | 100% | 297.819 | 297.819 | 68.4674 | 3Q18 | 4Q23 | -10 | 373.803 | -4.568%
Ivaí | 005/2016 (apr/2017) | 1 | Ivaí | Operational | 022/2017 | IE Ivaí | 50% | 1936.4738 | 968.2369 | 189.2949 | 4Q19 | 4Q22 | -3 | 1050.4335 | 9.501%
Tibagi |  | 5 | Tibagi | Operational | 026/2017 | IE Tibagi | 100% | 134.6464 | 134.6464 | 22.4741 | 3Q18 | 4Q20 | 8 | 117.526 | 20.16%
Itaquerê |  | 6 | Itaquerê | Operational | 027/2017 | IE Itaquerê | 100% | 397.7335 | 397.7335 | 67.218 | 3Q18 | 3Q20 | 11 | 255.906 | 40.78%
Aguapeí |  | 29 | Aguapeí | Operational | 046/2017 | IE Aguapeí | 100% | 601.8795 | 601.8795 | 75.9335 | 3Q19 | 1Q21 | 6 | 363.42 | 46.15%
Itapura-Bauru |  | 25 | Bauru | Operational | 042/2017 | IE Jaguar 6 | 100% | 125.7943 | 125.7943 | 15.3352 | 2Q18 | 3Q19 | 18 | 62.978 | 53.5%
Itapura-Lorena | 002/2018 (jun/2018) | 10 | Lorena | Operational | 021/2018 | IE Itapura | 100% | 237.947 | 237.947 | 17.3654 | 3Q19 | 4Q21 | 11 | 126.087 | 52.12%
Biguaçu |  | 1 | Biguaçu | Operational | 012/2018 | IE Biguaçu | 100% | 641.382 | 641.382 | 53.4445 | 1Q21 | 3Q22 | 13 | 455.965 | 38.89%
Minuano | 002/2019 (dec/2019) | 1 | Minuano | Operational | 001/2020 | Evrecy | 100% | 681.55 | 681.55 | 50.2175 | 1Q22 | - | 4 | 737.044 | 14%
Três lagoas |  | 6 | Três lagoas | Operational | 006/2020 | IE Tibagi | 100% | 98.792 | 98.792 | 7.0724 | 2Q21 | 2Q22 | 12 | 87.068 | 21.64%
Triângulo Mineiro |  | 7 | Triângulo Mineiro | Operational | 007/2020 | IEMG | 100% | 553.567 | 553.567 | 43.7515 | 1Q22 | 3Q23 | 20 | 519.595 | 23.63%
Riacho Grande | 001/2020 (dec/2020) | 7 | Riacho Grande | Under construction | 005/2021 | IE Riacho Grande | 100% | 1140.628 | 1140.628 | 88.4073 | 4Q23 | - | - | 530.1434 | -
Piraquê | 001/2022 (jun/2022) | 3 | Piraquê | Under construction | 008/2022 | ISA ENERGIA BRASIL | 100% | 3653.6077 | 3653.6077 | 325.7707 | 4Q23 | - | - | 1620.5335 | -
Jacarandá |  | 6 | Jacarandá | Under construction | 011/2022 | IE Jaguar 8 | 100% | 232.2923 | 232.2923 | 15.3151 | 4Q23 | - | - | 35.4809 | -
Lote 1 | 001/2023 (jun/2023) | 1 | Serra Dourada | Under construction | 006/2023 | ISA ENERGIA BRASIL | 100% | 3157 | 3157 | 305.553 | 3Q25 | - | - | 211.901 | -
| 001/2023 (jun/2023) | 7 | Itatiaia | Under construction | 012/2023 | ISA ENERGIA BRASIL | 100% | 2342.2975 | 2342.2975 | 235.6417 | 3Q25 | - | - | 95.892 | -
|  | 9 | Água Vermelha | Under construction | 014/2023 | IE Tibagi | 100% | 94.1769 | 94.1769 | 8.0324 | 2Q24 | ; | - | 34.813 | -
| Projects in Operation (12) | [7 empty] | 5164.7041 | 739.3011 | - | - | 2.5761 | 4680.73 | 23.2%
| Subsidiaries 100% in operation (9) | [7 empty] | 3771.1107 | 421.2796 | - | - | 7.1514 | 3099.392 | 30.52%
| Jointly Controlled Companies in Operation (3) | [7 empty] | 1393.5934 | 318.0215 | - | - | -3.4848 | 1581.338 | 4.219%
| Projects Under Construction (7) | [7 empty] | 10620.0024 | 978.7202 | - | - | - | 2528.7637 | -
| Total (19) | [6 empty] | 6558.2975 | 15784.7065 | 1718.0213 | - | - | 2.5761 | 7209.4937 | 23.2%