## Growth
Auctions | Project | Subsidiaries | % ISA CTEEP | Location | ANEEL CAPEX (R$ million) | ANEEL CAPEX ISA CTEEP Participation (R$ million) | Discount | RAP ISA CTEEP Cycle 2021/2022 (R$ million) | Contract signature | Implementation Deadline ANEEL | Necessity Date¹ | Environmental License (LI) | Initiation of Construction | Land Development4 | Projects Development5 | Entry in Commercial Operation
ANEEL
013/2015 10/28/2016 | Paraguaçú (Lote 3) | IE Paraguaçu | 50% | Bahia Minas Gerais | 510 | 255 | 0% | 65.2138 | 2017-02-10 | 2022-02-10 | 2019-01-01 | ü | 2Q19 | 100% | 95.5% | -
| Aimorés (Lote 4) | IE Aimorés | 50% | Minas Gerais | 341.1 | 170.55 | 0% | 43.6895 | 2017-02-10 | 2022-02-10 | 2019-01-01 | ü | 2Q19 | 100% | 97.2% | -
| Itaúnas (Lote 21) | IE Itaúnas | 100% | Espírito Santo | 297.8 | 297.8 | 25.14% | 57.7432 | 2017-02-10 | 2022-02-10 | 2018-07-01 | ü | 3Q18 | 100% | 80.15% | -
05/2016 4/24/2017 | Ivaí² (Lote 1) | IE Ivaí | 50% | Paraná | 1936.5 | 968.25 | 33.24% | 161.8258 | 2017-08-11 | 2022-08-11 | 2021-02-01 | ü | 4Q19 | 99% | 94.17% | -
| Tibagi (Lote 5) | IE Tibagi | 100% | São Paulo5 Paraná | 134.6 | 134.6 | 32.2% | 10.5242 | 2017-08-11 | 2021-08-11 | 2017-01-01 | ü | 3Q18 | 100% | 100% | 4Q20
| Itaquerê (Lote 6) | IE Itaquerê | 100% | São Paulo | 397.7 | 397.7 | 44.51% | 53.3471 | 2017-08-11 | 2021-08-11 | 2018-06-01 | ü | 3Q18 | 100% | 100% | 3Q20
| Aguapeí (Lote 29) | IE Aguapeí | 100% | São Paulo | 601.9 | 601.9 | 52.69% | 64.866 | 2017-08-11 | 2021-08-11 | 2018-12-01 | ü | 3Q19 | 100% | 100% | 1Q21
| Bauru (Lote 25) | IE Itapura | 100% | São Paulo (Bauru) | 125.8 | 125.8 | 57.55% | 12.5534 | 2017-08-11 | 2021-02-11 | 2019-08-01 | ü | 2Q18 | 100% | 100% | 3Q19
Auction 02/2018 06/29/2018 | Lorena (Lote 10) | IE Itapura | 100% | São Paulo (Lorena) | 238 | 238 | 73.9% | 41.6094 | 2018-09-21 | 2022-09-21 | 2020-01-01 | ü | 3Q19 | 100% | 100% | 4Q21
| Biguaçu (Lote 1) | IE Biguaçu | 100% | Santa Catarina | 641 | 641 | 66.7% | 44.5028 | 2018-09-21 | 2023-09-21 | 2021-09-01 | ü | 1Q21 | 100% | 88.74% | -
Auction 02/2019 12/19/2019 | Minuano (Lote 1) 6 | Evrecy | 100% | Rio Grande do Sul | 681.6 | 681.6 | 66.85% | 36.2517 | 2020-03-01 | 2024-12-01 | 2020-01-01 | 1Q22 | 1Q22 | 82% | 45.69% | -
| Três Lagoas (Lote 6) | IE Tibagi | 100% | Mato Grosso do Sul São Paulo | 98.8 | 98.8 | 68.12% | 5.8601 | 2020-03-01 | 2023-06-01 | 2020-01-01 | ü | 2Q21 | 96% | 94.21% | -
| Triângulo Mineiro (Lote 7) | IEMG | 100% | Minas Gerais | 553.6 | 553.6 | 65.4% | 11.7736 | 2020-03-01 | 2024-12-01 | 2020-01-01 | 4Q21 | 4Q21 | 93% | 38.41% | -
01/2020 12/17/2020 | Riacho Grande (Lote 7) | IE Riacho Grande | 100% | São Paulo | 1141 | 1141 | 57.9% | 73.2527 | 2021-03-01 | 2025-12-01 | 2026-01-01 | 2Q23 | 4Q23 | 50% | 20.96% | -
Total |  |  |  |  | 7699.4 | 6305.6 |  | 683.0132
¹ According to concession agreement
² To receive the total amount of RAP
3 Land Development: evolution of properties released
4 Project Development: evolution of all activities related to the project until electricity is provided to it
5 E Tibagi's RAP value does not consider adjustment resulting from the contractual amendment (-13.5%), approved by ANEEL's Board of Directors on 10/26/20
6 Obtaining parcial LI