## Growth
Auctions | Project | Subsidiaries | % ISA CTEEP | Location | ANEEL CAPEX (R$ million) | ANEEL CAPEX ISA CTEEP Participation (R$ million) | Discount | RAP ISA CTEEP Cycle 2021/2022 (R$ million) | Contract signature | Implementation Deadline ANEEL | Necessity Date¹ | Environmental License (LI) | Initiation of Construction | Land Development4 | Projects Development5 | Entry in Commercial Operation
ANEEL
013/2015 10/28/2016 | Paraguaçú (Lote 3) | IE Paraguaçu | 50% | Bahia Minas Gerais | 510 | 255 | 0% | 65.2138 | 2017-02-10 | 2022-02-10 | 2019-01-01 | ü | 2Q19 | 100% | 95.5% | -
| Aimorés (Lote 4) | IE Aimorés | 50% | Minas Gerais | 341.1 | 170.55 | 0% | 43.6895 | 2017-02-10 | 2022-02-10 | 2019-01-01 | ü | 2Q19 | 100% | 97.2% | -
| Itaúnas (Lote 21) | IE Itaúnas | 100% | Espírito Santo | 297.8 | 297.8 | 25.14% | 57.7432 | 2017-02-10 | 2022-02-10 | 2018-07-01 | ü | 3Q18 | 100% | 80.15% | -
05/2016 4/24/2017 | Ivaí² (Lote 1) | IE Ivaí | 50% | Paraná | 1936.5 | 968.25 | 33.24% | 161.8258 | 2017-08-11 | 2022-08-11 | 2021-02-01 | ü | 4Q19 | 99% | 94.17% | -
| Tibagi (Lote 5) | IE Tibagi | 100% | São Paulo5 Paraná | 134.6 | 134.6 | 32.2% | 10.5242 | 2017-08-11 | 2021-08-11 | 2017-01-01 | ü | 3Q18 | 100% | 100% | 4Q20
| Itaquerê (Lote 6) | IE Itaquerê | 100% | São Paulo | 397.7 | 397.7 | 44.51% | 53.3471 | 2017-08-11 | 2021-08-11 | 2018-06-01 | ü | 3Q18 | 100% | 100% | 3Q20
| Aguapeí (Lote 29) | IE Aguapeí | 100% | São Paulo | 601.9 | 601.9 | 52.69% | 64.866 | 2017-08-11 | 2021-08-11 | 2018-12-01 | ü | 3Q19 | 100% | 100% | 1Q21
| Bauru (Lote 25) | IE Itapura | 100% | São Paulo (Bauru) | 125.8 | 125.8 | 57.55% | 12.5534 | 2017-08-11 | 2021-02-11 | 2019-08-01 | ü | 2Q18 | 100% | 100% | 3Q19
Auction 02/2018 06/29/2018 | Lorena (Lote 10) | IE Itapura | 100% | São Paulo (Lorena) | 238 | 238 | 73.9% | 11.7736 | 2018-09-21 | 2022-09-21 | 2020-01-01 | ü | 3Q19 | 100% | 100% | 4Q21
| Biguaçu (Lote 1) | IE Biguaçu | 100% | Santa Catarina | 641 | 641 | 66.7% | 44.5028 | 2018-09-21 | 2023-09-21 | 2021-09-01 | ü | 1Q21 | 100% | 88.74% | -
Auction 02/2019 12/19/2019 | Minuano (Lote 1) 6 | Evrecy | 100% | Rio Grande do Sul | 681.6 | 681.6 | 66.85% | 41.6094 | 2020-03-01 | 2024-12-01 | 2020-01-01 | 1Q22 | 1Q22 | 82% | 45.69% | -
| Três Lagoas (Lote 6) | IE Tibagi | 100% | Mato Grosso do Sul São Paulo | 98.8 | 98.8 | 68.12% | 5.8601 | 2020-03-01 | 2023-06-01 | 2020-01-01 | ü | 2Q21 | 96% | 94.21% | -
| Triângulo Mineiro (Lote 7) | IEMG | 100% | Minas Gerais | 553.6 | 553.6 | 65.4% | 36.2517 | 2020-03-01 | 2024-12-01 | 2020-01-01 | 4Q21 | 4Q21 | 93% | 38.41% | -
01/2020 12/17/2020 | Riacho Grande (Lote 7) | IE Riacho Grande | 100% | São Paulo | 1141 | 1141 | 57.9% | 73.2527 | 2021-03-01 | 2025-12-01 | 2026-01-01 | 2Q23 | 4Q23 | 50% | 20.96% | -
Total |  |  |  |  | 7699.4 | 6305.6 |  | 683.0132
¹ According to concession agreement
² To receive the total amount of RAP
3 Land Development: evolution of properties released
4 Project Development: evolution of all activities related to the project until electricity is provided to it
5 E Tibagi's RAP value does not consider adjustment resulting from the contractual amendment (-13.5%), approved by ANEEL's Board of Directors on 10/26/20
6 Obtaining parcial LI

## Subsidiárias Eng
|  |  | Company | Phase | Location | RAP Cycle 2021/2022¹ (R$ million) | RAP ISA CTEEP Cycle 2021/2022 (R$ million) | Profit Regime² | Share (%) | Consolidation
Categoria | Projeto
CTEEP | ISA CTEEP | 1 | ISA CTEEP | Operational | São Paulo | 2320.1203 | 2320.1203 | Real Profit | ISA CTEEP 100% | Fully consolidated
Licitada Antiga | IE Madeira | 2 | IE Madeira | Operational | Rondônia / SP | 577.6167 | 294.5845 | Real Profit | ISA CTEEP 51% / Furnas 24,5% / Chesf 24,5% | Equity method
Licitada Nova | IE Ivaí | 3 | IE Ivaí | Under construction | Paraná | 323.6516 | 161.8258 | Real Profit | ISA CTEEP 50% / TAESA 50% | Equity method
M&A | PBTE | 4 | PBTE | Operational | São Paulo | 179.1121 | 179.1121 | Real Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | IE Paraguaçu | 5 | IE Paraguaçu | Under construction | Bahia / MG | 130.4275 | 65.2138 | Real Profit | ISA CTEEP 50% / TAESA 50% | Equity method
Licitada Antiga | IE Garanhuns | 6 | IE Garanhuns | Operational | Pernambuco | 100.1592 | 51.0812 | Real Profit | ISA CTEEP 51% / Chesf 49% | Equity method
Licitada Nova | IE Aimorés | 7 | IE Aimorés | Under construction | Minas Gerais | 87.379 | 43.6895 | Real Profit | ISA CTEEP 50% / TAESA 50% | Equity method
Licitada Nova | IE Riacho Grande | 8 | IE Riacho Grande | Under construction | São Paulo | 73.2527 | 73.2527 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Antiga | IE Pinheiros | 9 | IE Pinheiros | Operational | São Paulo | 69.2116 | 69.2116 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Antiga | IE Serra do Japi | 10 | IE Serra do Japi | Operational | São Paulo | 64.8899 | 64.8899 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | IE Aguapeí | 11 | IE Aguapeí | Operational | São Paulo | 64.866 | 64.866 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | IE Itaquerê | 12 | IE Itaquerê | Operational | São Paulo | 53.3471 | 53.3471 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
M&A | Evrecy | 13 | Evrecy | Operational | Espírito Santo | 17.4165 | 17.4165 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | Minuano |  | 0 | Under construction | Rio Grande do Sul | 41.6094 | 41.6094 | Presumed Profit | 0 | Equity method
Licitada Nova | IE Itaúnas | 14 | IE Itaúnas | Under construction | Espírito Santo | 57.7432 | 57.7432 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Antiga | IEMG | 15 | IEMG | Operational | Minas Gerais | 21.0008 | 21.0008 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | Triângulo Mineiro |  | 0 | Under construction | Minas Gerais | 36.2517 | 36.2517 | Presumed Profit | 0 | Equity method
Licitada Antiga | IENNE | 16 | IENNE | Operational | Tocantins | 55.7305 | 55.7305 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | IE Biguaçu | 17 | IE Biguaçu | Under construction | Santa Catarina | 44.5028 | 44.5028 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | Itapura-Bauru | 18 | IE Itapura | Operational | São Paulo (Bauru) | 12.5534 | 12.5534 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | Itapura-Lorena |  | 0 | Operational | São Paulo (Lorena) | 11.7736 | 11.7736 | Presumed Profit | 0 | Equity method
Licitada Antiga | IE Sul | 19 | IE Sul | Operational | Rio Grande do Sul | 22.0485 | 22.0485 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | IE Tibagi | 20 | IE Tibagi | Operational | SP / Paraná3 | 10.5242 | 10.5242 | Presumed Profit | ISA CTEEP 100% | Fully consolidated
Licitada Nova | Três Lagoas | 21 | 0 | Under construction | Mato Grosso do Sul / SP | 5.8601 | 5.8601 | Presumed Profit | 0 | Equity method
|  |  | Total |  |  | 4381.0484 | 3778.2091
¹ 2021/2022 revenue cycle includes adjustment parcel (“PA”), net of PIS and COFINS
² Presumed Profit: tax regime where the income tax is 25% on the presumed 8% of operating income and social contribution tax is 9% over the presumed 12% on Real Profit: tax regime where Income Tax and Social Security Contribution totals 34% on income
³ IE Tibagi RAP considers adjustment resulting from the contractual amendment (-13.5%), approved by the ANEEL Board of Directors on 10/26/20
[6 empty] | Check | 0